## Slide 1
1. TRANSFORMATION ROADMAP
Phased Agile Rollout & Milestone Gate Schedule
De-risking enterprise cutover through incremental multi-plant waves.
Schneider Electric • Enterprise Delivery Roadmap • Enterprise Architecture Advisory
01 / 03
PHASE 1 • WEEKS 1-4
Blueprint & Edge Setup
• OPC-UA Edge Config
• SAP BTP Subaccount Setup
• Pilot Line Connect
GATE: GATE 1: Latency <250ms
PHASE 2 • WEEKS 5-10
Core MES Integration
• Production Order Dispatch
• Electronic Traveler UI
• QA Inspection Gates
GATE: GATE 2: Zero RFC Buffer Leaks
PHASE 3 • WEEKS 11-16
Enterprise Rollout
• Lines 2-6 Cutover
• Operator Enablement
• Hypercare Support
GATE: GATE 3: Final Acceptance

## Slide 2
2. CONTROL GATES
Milestone Quality & Acceptance Gates
Formal criteria required before transitioning between project phases.
Schneider Electric • Enterprise Delivery Roadmap • Enterprise Architecture Advisory
02 / 03
GATE 01
Architecture Blueprint
[✓] BTP event mesh sized
[✓] Clean-core APIs catalogued
[✓] Security boundaries approved
OWNER: Chief Architect
GATE 02
Pilot Line Deployment
[✓] Work-center dispatch live
[✓] Inline vision cameras tested
[✓] Zero dropped telemetry
OWNER: Plant Director
GATE 03
Quality Certification
[✓] 21 CFR Part 11 signed
[✓] Genealogy tree validated
[✓] Audit trail verified
OWNER: VP Quality
GATE 04
Enterprise Go-Live
[✓] Multi-plant cutover completed
[✓] Real-time 101 posting live
[✓] Hypercare SLA active
OWNER: Steering Committee

## Slide 3
3. TIMELINE TRACK
Program Delivery Schedule & Major Workstreams
Chronological milestone progression across four delivery months.
Schneider Electric • Enterprise Delivery Roadmap • Enterprise Architecture Advisory
03 / 03
MONTH 1
Sprint 0: Architecture Blueprint
BTP subaccounts & OT edge configuration
MONTH 2
Sprint 1-2: Pilot Line Deployment
CNC machining cell connected & telemetry live
MONTH 3
Sprint 3-4: Quality & Genealogy
Electronic batch record & camera inspection live
MONTH 4
Sprint 5-6: Enterprise Cutover
Full plant rollout & 24/7 hypercare transition