## Slide 1
1. SCOPE MATRIX
Commercial Scope & Boundary Matrix: Commercial proposal
DECISION INTENT: SCOPE MATRIX mapped for ABB Robotics Global Division operational architecture.
ABB Robotics Global Division • Commercial Proposal • Enterprise Architecture Advisory
01 / 06
EVALUATION CRITERIA | In-Scope (Turnkey) | Customer Responsibility | Out-of-Scope (Phase 2)
SAP BTP Event Mesh Setup | FULL (Turnkey) | PARTIAL (Access) | NO
OPC-UA Machine Telemetry | FULL (Turnkey) | PARTIAL (Network) | NO
Electronic Batch Records | FULL (Turnkey) | PARTIAL (SOP Sign-off) | NO
Multi-Site Cloud Rollout | NO | NO | RECOMMENDED

## Slide 2
2. MILESTONE GATES
Milestone Gates & Quality Criteria: Commercial proposal
DECISION INTENT: MILESTONE GATES mapped for ABB Robotics Global Division operational architecture.
ABB Robotics Global Division • Commercial Proposal • Enterprise Architecture Advisory
02 / 06
GATE 01
Architecture Blueprint
[✓] BTP event mesh sized
[✓] Clean-core APIs catalogued
[✓] Security boundaries approved
OWNER: Chief Architect
GATE 02
Pilot Line Deployment
[✓] Work-center dispatch live
[✓] Inline vision cameras tested
[✓] Zero dropped telemetry
OWNER: Plant Director
GATE 03
Quality Certification
[✓] 21 CFR Part 11 signed
[✓] Genealogy tree validated
[✓] Audit trail verified
OWNER: VP Quality
GATE 04
Enterprise Go-Live
[✓] Multi-plant cutover completed
[✓] Real-time 101 posting live
[✓] Hypercare SLA active
OWNER: Steering Committee

## Slide 3
3. COMMERCIAL TERMS
Commercial Model & Milestone Payment Gates: Commercial proposal
DECISION INTENT: COMMERCIAL TERMS mapped for ABB Robotics Global Division operational architecture.
ABB Robotics Global Division • Commercial Proposal • Enterprise Architecture Advisory
03 / 06
PHASE / MILESTONE | KEY DELIVERABLE & ACCEPTANCE | TIMELINE | BILLING % | INVESTMENT
Phase 1: Architecture Blueprint | Architecture blueprint & security sign-off | Weeks 1-3 | 25% | $85,000
Phase 2: Pilot Implementation | Pilot line integration & telemetry validation | Weeks 4-8 | 35% | $119,000
Phase 3: Plant Rollout | Full plant cutover & operator enablement | Weeks 9-14 | 30% | $102,000
Phase 4: Final Acceptance | 30-day hypercare completion & ledger audit | Weeks 15-16 | 10% | $34,000
TOTAL ENGAGEMENT |  |  | 100% | $340,000 Turnkey Fixed Investment

## Slide 4
4. ASSUMPTIONS REGISTER
Operational Assumptions & Commitments: Commercial proposal
DECISION INTENT: ASSUMPTIONS REGISTER mapped for ABB Robotics Global Division operational architecture.
ABB Robotics Global Division • Commercial Proposal • Enterprise Architecture Advisory
04 / 06
ID | ACTION ITEM DESCRIPTION | WORKSTREAM | PRIORITY | OWNER | DUE DATE | STATUS
ACT-01 | Recalibrate torque load cells on Station 20 | Maintenance | HIGH | Lead Tech | Week 2 | IN PROGRESS
ACT-02 | Implement automated ASN barcode validation in ERP | Integration | HIGH | BTP Lead | Week 3 | OPEN
ACT-03 | Conduct operator Poka-Yoke ergonomics review | Plant Ops | MED | Supervisor | Week 4 | OPEN
ACT-04 | Publish updated First Pass Yield dashboard to CXO | Analytics | MED | Data Arch | Week 1 | COMPLETED

## Slide 5
5. RACI ALIGNMENT
Program Dependencies & RACI Alignment: Commercial proposal
DECISION INTENT: RACI ALIGNMENT mapped for ABB Robotics Global Division operational architecture.
ABB Robotics Global Division • Commercial Proposal • Enterprise Architecture Advisory
05 / 06
ACTIVITY / DELIVERABLE | Advisory Architect | Client IT Lead | Plant Operations Lead | Steering Committee
System Architecture & BTP Sizing | A | R | C | I
OT Network & Firewall Exceptions | C | A | R | I
Operator Enablement & SOP Sign-off | R | C | A | I
Milestone Gate Sign-off & Invoicing | C | C | C | A

## Slide 6
6. PROGRAM SCHEDULE
Execution Timeline & Deliverable Milestones: Commercial proposal
DECISION INTENT: PROGRAM SCHEDULE mapped for ABB Robotics Global Division operational architecture.
ABB Robotics Global Division • Commercial Proposal • Enterprise Architecture Advisory
06 / 06
MONTH 1
Sprint 0: Architecture Blueprint
BTP subaccounts & OT edge configuration
MONTH 2
Sprint 1-2: Pilot Line Deployment
CNC machining cell connected & telemetry live
MONTH 3
Sprint 3-4: Quality & Genealogy
Electronic batch record & camera inspection live
MONTH 4
Sprint 5-6: Enterprise Cutover
Full plant rollout & 24/7 hypercare transition