## Slide 1
1. SCOPE MATRIX
Turnkey Implementation Scope & Boundary Matrix
Clear demarcations of advisory deliverables vs. client prerequisites.
Siemens Energy • Enterprise Structured Tables • Enterprise Architecture Advisory
01 / 03
EVALUATION CRITERIA | In-Scope (Turnkey) | Client Responsibility | Out-of-Scope (Phase 2)
SAP BTP Event Mesh Setup | FULL (Turnkey) | PARTIAL (Access) | NO
OPC-UA Machine Telemetry | FULL (Turnkey) | PARTIAL (Network) | NO
Electronic Batch Records | FULL (Turnkey) | PARTIAL (SOP Sign-off) | NO
Multi-Site Cloud Rollout | NO | NO | RECOMMENDED

## Slide 2
2. COMMERCIAL MODEL
Milestone Invoicing Schedule & Payment Gates
Fixed-price engagement with payments tied strictly to certified deliverables.
Siemens Energy • Enterprise Structured Tables • Enterprise Architecture Advisory
02 / 03
PHASE / MILESTONE | KEY DELIVERABLE & ACCEPTANCE | TIMELINE | BILLING % | INVESTMENT
Phase 1: Architecture Blueprint | Architecture blueprint & security sign-off | Weeks 1-3 | 25% | $85,000
Phase 2: Pilot Implementation | Pilot line integration & telemetry validation | Weeks 4-8 | 35% | $119,000
Phase 3: Plant Rollout | Full plant cutover & operator enablement | Weeks 9-14 | 30% | $102,000
Phase 4: Final Acceptance | 30-day hypercare completion & ledger audit | Weeks 15-16 | 10% | $34,000
TOTAL ENGAGEMENT |  |  | 100% | $340,000 Turnkey Fixed Investment

## Slide 3
3. RISK REGISTER
Enterprise Risk Mitigation & Contingency Radar
Quantified severity and pre-engineered hedging strategies.
Siemens Energy • Enterprise Structured Tables • Enterprise Architecture Advisory
03 / 03
ID | RISK EVENT / VULNERABILITY | SEVERITY | LIKELIHOOD | SCORE | MITIGATION STRATEGY | OWNER
RSK-01 | OT firewall change freeze delays pilot line connect | HIGH | MED | CRITICAL | Pre-authorize security exceptions via ARB charter | CISO
RSK-02 | Legacy PLC firmware incompatible with OPC-UA daemon | MED | LOW | MODERATE | Deploy industrial edge protocol translation gateway | OT Lead
RSK-03 | Operator pushback against biometric sign-off | LOW | MED | LOW | Provide RFID badge tap alternative with supervisor PIN | HR Lead